## Slide 1: 2023 Fellowship Project Presentation
Aaron Maloy
IT Manager
Clay County Hospital

## Slide 2
Core Statement
My organization, Clay County Hospital, is developing a remote patient monitoring solution for nursing staff to proactively monitor patients to mitigate patient falls and to combat nursing staff shortages.

## Slide 3
Planning
Review current market and solutions
  Mobile camera carts
  Analytic software
  Very costly
Stakeholder buy-in
  Bi-weekly meetings
Proposed Solution
  Hikvision PTZ cameras
  Hikvision monitoring software
  Isolated network for security
  No recording functionality
Stakeholders
Administration Team
Nursing Management Team
Forms Committee
Hospital Board Committee
IT Team

## Slide 4
Deliverables
Budget
Equipment installation
Update patient consent forms
Signage in patient rooms
Nursing staff training
Successes
Implemented at a substantial lower cost compared to 3rd party vendors
Created and implemented by local IT
Barriers
Formal project plan was not followed
Ceiling supporting cameras
Timeline expectation was extended due to other ongoing projects
Monitoring software has limitations (freeware)

## Slide 5
Outcomes to Date
Project went live February 20th
Continuous Improvement
  Secondary cameras in patient rooms with double beds
  Testing of different cameras with wider angle lens
  3rd party monitoring software
Lessons Learned
Follow detailed project plan
  Scope statement

## Slide 6
Mentor
Sue Odle - VP/Administrator - St. Joseph Memorial Hospital
Thank You!
CCH Administration
CCH Nursing Staff
CCH IT Team
Fellowship program

## Slide 7: Questions?
Notes: Notes